Finger Joint KL Classification & Generation Project

Meeting Minutes, Experiments, and Results (Week 1–2)

1. Project Overview

This document presents a consolidated report of the first two weeks of the Finger Joint KL Classification & Generation project. It includes data preprocessing, model development (CVAE, CGAN, LDM), initial classification experiments, and a strategy for data augmentation guided by model performance.

2. Team Members and Responsibilities

| Team Member | Responsibility |
| --- | --- |
| Yuxuan Huang | CVAE (Conditional Variational Autoencoder) |
| Weihan Chen | CGAN (Conditional GAN) |
| Ke Pan | LDM (Latent Diffusion Model) |

3. Week 1 – Data Preprocessing

3.1 Data Cleaning & Alignment

- Removed invalid/missing KL labels

- Matched image filenames with Excel metadata (ID-based join)

- Verified data integrity and file paths

3.2 Missing Value Handling

- JSN / OP / ME → median imputation

- ER / CY → filled with 0

- PW → mean/median based on distribution

3.3 Class Distribution Analysis

| KL Grade | Count (Example) |
| --- | --- |
| KL0–2 | High (majority) |
| KL3–4 | Very low (minority) |

Insight: Severe class imbalance → expected poor performance on KL3–4.

4. Week 2 – Model Development & Evaluation

4.1 Generative Models (Individual Work)

CVAE (Yuxuan Huang)

- Baseline CVAE implemented

- Initial issue: blurry reconstructions (especially KL3–4)

CGAN (Weihan Chen)

- Conditional GAN implemented

- Sharper images but training instability observed

LDM (Ke Pan)

- Latent diffusion pipeline built

- Highest visual quality among three models

4.2 Classification Model (Joint Work)

Purpose:

- Evaluate baseline performance

- Determine whether data augmentation is necessary

- Identify important joints for classification

5. Experimental Results (Initial)

5.1 Baseline Classification Performance

| Dataset | Accuracy | F1-score | KL3–4 TPR |
| --- | --- | --- | --- |
| Original Only | 0.XX | 0.XX | Low |

5.2 Model Comparison (Generated Images)

| Model | Visual Quality | Sharpness | Stability |
| --- | --- | --- | --- |
| CVAE | Low–Medium | Blurry | High |
| CGAN | Medium–High | Sharp | Medium |
| LDM | High | Very Sharp | Medium |

5.3 Classification with Augmented Data (Planned/Partial)

| Dataset | Accuracy | F1-score | KL3–4 TPR |
| --- | --- | --- | --- |
| + CVAE Data | TBD | TBD | TBD |
| + CGAN Data | TBD | TBD | TBD |
| + LDM Data | TBD | TBD | TBD |

6. Key Insight – Joint Importance

Critical Finding:

PIP joints (PIP2–PIP4) contribute significantly more to classification performance.

Reasoning:

- Stronger structural deformation in severe KL grades

- More discriminative visual patterns

- Other joints introduce noise

7. Strategic Decision

7.1 Pipeline Direction

- Use LDM as primary model

- Use CGAN and CVAE as baselines

7.2 Data Strategy

- Focus on KL3–4 augmentation

- Potentially generate ROI-based images (PIP joints only)

8. Figures (Insert in Word)

Figure 1 – Model Outputs Comparison

(Insert images side-by-side)

- CVAE vs CGAN vs LDM

Figure 2 – Classification Performance

(Insert confusion matrix or bar chart)

9. Plan for Next Week

9.1 Model Improvements

CVAE

- L1 loss + SSIM

- Better decoder architecture

CGAN

- Improve stability and diversity

LDM

- Optimize training

- Generate large KL3–4 dataset

9.2 Classification Pipeline

- Train with augmented data

- Evaluate:

  - Accuracy

  - F1-score

  - TPR per class

10. Summary

Over two weeks, the team:

- Completed data preprocessing

- Built three generative models

- Developed baseline classifier

- Identified PIP joints as critical features

- Established LDM as the main approach

The project is now transitioning toward improving classification performance using high-quality synthetic data.

Appendix (Optional for Submission)

A. Code Link

(Insert Colab / GitHub link)

B. Notes

- Replace all TBD / placeholder values with actual results

- Insert figures before submission